## Instructions
For detail regarding the practice of Requirements Management, please refer to the Requirements Management Practices Guide
Instructions For Completing This Document
1.) | Complete the Project Name, C/I/O, Project Manager Name, and Project Description fields
2.) | For each issue identified, complete the following:
ID: A unique ID number used to identify the traceability item in the requirements traceability matrix.
Associated ID(s): This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Technical Assumption(s) or Customer Need(s): This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Functional Requirement: This column should be populated with a description of the functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Architectural/Design Document: This column should be populated with a description of the architectural/design document linked to the functional requirement.
Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Tested In: This column should be populated with the module that the functional requirement has been tested in.
Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Verification: This column should be populated with a description of the verification document linked to the functional requirement.
Additional Comments: This column should be populated with any additional comments

## Functional
REQUIREMENTS TRACEABILITY MATRIX | [7 empty] | REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Schedule 360 | [5 empty] | Project Name: |  | <optional>
Class: |  | Advanced Requirements Engineering | [5 empty] | Class: |  | <required>
Team Name: |  | Alpha | [5 empty] | Team Name: |  | <required>
Professor: |  | Dr. Lawrence Chung | [5 empty] | Professor: |  | <required>
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Functional Requirement | Status | Traceability Reference | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
VERSION 1
001 | 2.2.1 | Compatibility | The application shall be compatile with all existing electronic calendars. | In Progress | Move to non functional
002 | 2.2.2 | Interface | The application shall allow users to synchronize information between the application and all other existing electronic calendars (personal, work, etc.). | In Progress | [8 empty] | Moved to non-functional req 026 V2
003 | 2.2.3 | Create appointments | The application shall allow the user to create appointments. | In Progress
004 | 2.2.4 | View appointments | The application will display all of the user’s appointments. | In Progress
005 | 2.2.5 | View appointments | The application shall allow the user to select what format to display the information. | In Progress
006 | 2.2.6 | Interface | The application shall allow it’s users to interface with the application via their smart phones or tablets. | In Progress
007 | 2.2.7 | Accessibility | The application will be maintained on a server accessible through the cloud. | In Progress | [8 empty] | Moved to non-functional req 017 V2, accessibility is a non-functional requirment.
008 | 2.2.8 | Security | The application shall allow users to create an account with password in order to create/access their information via the cloud. | In Progress | [8 empty] | Moved to non-functional req 025 & 027 V2, security is a non-functional requirment.
009 | 2.2.9 | Update Calendar | The user shall be able to specify which calendar is updated. | In Progress
010 | 2.2.10 | ID Conflicts | The application shall provide a warning if a scheduling conflict exists. | In Progress
VERSION 2
011 | 2.2.1 | Interface | The application shall allow users to synchronize information between the application and all other existing electronic calendars (personal, work, etc.). | In Progress | 2.2.2 v1 | [7 empty] | Moved to non-functional req 035 V2, compatibility is a non-functional requirement.
012 | 2.2.2 | Create appointments | The application shall allow the user to create appointments. | In Progress | 2.2.3 v1
013 | 2.2.3 | Create appointments | The appointment shall allow the creator to specify the subject of the appointment. | In Progress | New | [7 empty] | Need requirements which clearly define the fields needed to create appointments.
014 | 2.2.4 | Create appointments | The appointment shall allow the creator to specifiy the location of the appointment. | In Progress | New
015 | 2.2.5 | Create appointments | The appointment shall allow the user to specify the start date of the appointment. | In Progress | New
016 | 2.2.6 | Create appointments | The appointment shall allow the creator to specify the end date of the appointment. | In Progress | New
017 | 2.2.7 | Create appointments | The appointment shall allow the user to specify the start time of the appointment in hours and minutes. | In Progress | New
018 | 2.2.8 | Create appointments | The appointment shall allow the creator to specify the end time of the appointment in hours and minutes. | In Progress | New
019 | 2.2.9 | Create appointments | The appointment shall allow the creator to place notes in the appoinment. | In Progress | New
020 | 2.2.10 | Create appointments | The appointment shall allow the creator to set a reminder alarm. | In Progress | New
021 | 2.2.11 | Create appointments | The appointment shall allow the creator the ability to invite others via email. | In Progress | New
022 | 2.2.13 | Create appointments | The appointment shall allow the creator to set future reoccurrences. | In Progress | New
023 | 2.2.14 | Create appointments | The appointment shall allow the creator to set their availability as Busy, Free, Tentative, and Out of the Office. | In Progress | New
024 | 2.2.15 | Create appointments | The appointment shall allow the creator to attach files to the appointment. | In Progress | New
025 | 2.2.16 | View appointments | The user shall be able to select the display for all appointments as a List, Daily, Weekly, or Monthly view | In Progress | 2.2.4 & 2.2.5 v1 combined
026 | 2.2.17 | Interface | The application shall allow users to interface with it on the Apple iPhone and iPad. | In Progress | 2.2.6 v1 | [7 empty] | Combined requirements 004 & 005 from version 1 (V1).
027 | 2.2.18 | Accessibility | The application will be maintained on a server accessible through the cloud. | In Progress | 2.2.7 v1 | [7 empty] | Moved to non-functional requirement 2.3.14 V3.
028 | 2.2.19 | Security | The application shall allow users to create an account with password in order to create/access their information via the cloud. | In Progress | 2.2.8 v1 | [7 empty] | Moved to non-functional requirement 2.3.12 V2 due to security requirement.
029 | 2.2.20 | Update Calendar | The user shall be able to specify which calendar is updated. | In Progress | 2.2.9 v1
030 | 2.2.21 | ID Conflicts | The application shall provide a warning if a scheduling conflict exists. | In Progress | 2.2.10 v1
031 | 2.2.22 | Interface | The application shall have a search function. | In Progress | New
032 | 2.2.23 | Interface | The application shall allow the user to sort it by location, start date, end date, start time, and end time. | In Progress | New
033 | 2.2.24 | Interface | The application shall allow users to modify or edit the fields of an existing appointment. | In Progress | New
034 | 2.2.25 | Interface | The application shall allow users to delete appointments | In Progress | New
035 | 2.2.26 | Update Software | The software shall be updateable. | In Progress | New
036 | 2.2.27 |  |  | In Progress
037 | 2.2.28 |  |  | In Progress
038 | 2.2.29 |  |  | In Progress
039 | 2.2.30 |  |  | In Progress
VERSION 3
040 | 2.2.1 | Interface | The application shall allow users to synchronize information between the application and all other existing electronic calendars (personal, work, etc.). | In Progress | 2.2.1 V2 |  |  |  | 2 |  |  |  | Revised to functional requirement of synchronization
041 | 2.2.2 | Create appointments | The application shall allow the user to create appointments. | In Progress | 2.2.2 V2 |  |  |  | 10
042 | 2.2.3 | Create appointments | The appointment shall allow the creator to specify the subject of the appointment. | In Progress | 2.2.3 V2 |  |  |  | 10
043 | 2.2.4 | Create appointments | The appointment shall allow the creator to specify the location of the appointment. | In Progress | 2.2.4 V2 |  |  |  | 10
044 | 2.2.5 | Create appointments | The appointment shall allow the user to specify the start date of the appointment. | In Progress | 2.2.5 V2 |  |  |  | 10
045 | 2.2.6 | Create appointments | The appointment shall allow the creator to specify the end date of the appointment. | In Progress | 2.2.6 V2 |  |  |  | 10
046 | 2.2.7 | Create appointments | The appointment shall allow the user to specify the start time of the appointment in hours and minutes. | In Progress | 2.2.7 V2 |  |  |  | 10
047 | 2.2.8 | Create appointments | The appointment shall allow the creator to specify the end time of the appointment in hours and minutes. | In Progress | 2.2.8 V2 |  |  |  | 10
048 | 2.2.9 | Create appointments | The appointment shall allow the creator to place notes in the appointment. | In Progress | 2.2.9 V2 |  |  |  | 10
049 | 2.2.10 | Create appointments | The appointment shall allow the creator to set a reminder alarm. | In Progress | 2.2.10 V2 |  |  |  | 10
050 | 2.2.11 | Create appointments | The appointment shall allow the creator the ability to invite others via email. | In Progress | 2.2.11 V2 |  |  |  | 10
051 | 2.2.12 | Create appointments | The appointment shall allow the creator to set future reoccurrences. | In Progress | 2.2.13 V2 |  |  |  | 10
052 | 2.2.13 | Create appointments | The appointment shall allow the creator to set their availability as Busy, Free, Tentative, and Out of the Office. | In Progress | 2.2.14 V2 |  |  |  | 10
053 | 2.2.14 | Create appointments | The appointment shall allow the creator to attach files to the appointment. | In Progress | 2.2.15 V2 |  |  |  | 10
054 | 2.2.15 | View appointments | The user shall be able to select the display for all appointments as a List, Daily, Weekly, or Monthly view | In Progress | 2.2.16 V2 |  |  |  | 11
055 | 2.2.16 | Interface | The application shall allow users to interface with it on the Apple iPhone and iPad. | In Progress | 2.2.17 V2 |  |  |  | 3
056 | 2.2.17 | Update Calendar | The user shall be able to specify which calendar is updated. | In Progress | 2.2.20 V2 |  |  |  | 4
057 | 2.2.18 | ID Conflicts | The application shall provide a warning if a scheduling conflict exists. | In Progress | 2.2.21 V2 |  |  |  | 12
058 | 2.2.19 | Interface | The application shall have a search function. | In Progress | 2.2.22 V2 |  |  |  | 5
059 | 2.2.20 | Interface | The application shall allow the user to sort it by location, start date, end date, start time, and end time. | In Progress | 2.2.23 V2 |  |  |  | 6
060 | 2.2.21 | Interface | The application shall allow users to modify or edit the fields of an existing appointment. | In Progress | 2.2.24 V2 |  |  |  | 7
061 | 2.2.22 | Interface | The application shall allow users to delete appointments | In Progress | 2.2.25 V2 |  |  |  | 8
062 | 2.2.23 | Update Software | The software shall be updateable. | In Progress | 2.2.26 V2 |  |  |  | 9
063 | 2.2.24 | Interface | The calendar shall allow registration online from www.360schedule.com. | In Progress | New |  |  |  | 1
Note on A6: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B6: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C6: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on D6: • Functional Requirement: This column should be populated with a description of the functional requirement.
Note on E6: • Status: This column should be populated with the current status of the functional requirement.
Note on F6: •Traceability Reference: This column should be populated with a description of the architectural/ design document linked to the functional requirement.
Note on G6: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on H6: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Note on I6: • Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Note on J6: • Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Note on K6: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on L6: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on M6: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.

## Non-Functional
REQUIREMENTS TRACEABILITY MATRIX | [7 empty] | REQUIREMENTS TRACEABILITY MATRIX
Project Name: |  | Schedule 360 | [5 empty] | Project Name: |  | <optional>
Class: |  | Advanced Requirements Engineering | [5 empty] | Class: |  | <required>
Team Name: |  | Alpha | [5 empty] | Team Name: |  | <required>
Professor: |  | Dr. Lawrence Chung | [5 empty] | Professor: |  | <required>
ID | Assoc ID | Technical Assumption(s) and/or Customer Need(s) | Non-Functional Requirement | Status | Traceability Reference | Technical Specification | System Component(s) | Software Module(s) | Test Case Number | Tested In | Implemented In | Verification | Additional Comments
VERSION 1
001 | 2.3.1 | portability | The software shall be compatible on smartphones with wireless internet connectivity. | In Progress
002 | 2.3.2 | availability | The software shall be available for download from a database containing the Schedule 360 smartphone application. | In Progress
003 | 2.3.3 | compatibility | The filesize of the software application shall not exceed 20 MB. | In Progress
004 | 2.3.4 | usability | The software shall be understandable to users familiar with software scheduling functions. | In Progress
005 | 2.3.5 | usability | The software functions shall be accessible through a GUI application interface. | In Progress
006 | 2.3.6 | low power consumption, performance | The software shall perform greater than 95% of its computations in the cloud. | In Progress
007 | 2.3.7 | flexibility | The software shall have the flexibility to operate on the following smartphone platforms: Symbian, iPhone, Android, Windows, Blackberry. | In Progress | combine with 2.3.1
008 | 2.3.8 | security | The software shall allow no more than one user to access a given profile at a time. | In Progress
009 | 2.3.9 | security | The software shall contain a password security feature with a user interface. | In Progress | move to functional
010 | 2.3.10 | security and modifiability | The software security feature shall be modifiable by the user in order to change the password. | In Progress
011 | 2.3.11 | maintainability | The software shall be maintainable using software updates. | In Progress
012 | 2.3.12 | portability | Software updates shall be applied wirelessly through an internet connection. | In Progress
013 | 2.3.13 | maintainability | Software updates shall prompt the user to accept the update before proceeding. | In Progress
014 | 2.3.14 | performance | The software shall perform output within 0.5 seconds any user function. | In Progress
015 | 2.3.15 | correctness | The software shall output correct scheduling information from communicable devices. | In Progress
VERSION 2
016 | 2.3.1 | portability | The software shall be compatible as an application on the Apple iPhone version 3GS and newer. | In Progress | 2.3.1
017 | 2.3.2 | availability | The software shall be available for download from the iPhone App Store. | In Progress | 2.3.2
018 | 2.3.3 | compatibility | The filesize of the application shall not exceed the maximum limit for iPhone apps transmitted over a 3G connection. | In Progress | 2.3.3
019 | 2.3.4 | usability | The software shall be understandable to users who perform scheduling functions on a daily basis. | In Progress | 2.3.4
020 | 2.3.5 | usability | The software functions shall be accessible through a GUI application interface. | In Progress | 2.3.5
021 | 2.3.6 | usability | The GUI application interface shall have an ease of use such that the user can begin performing operations without prior training or exposure to the application. | In Progress | New
022 | 2.3.7 | usability | The GUI application interface shall have readable text such that a user with 20/20 eyesight or corrected vision can read the text in ambient lighting from a distance of 6 inches to 24 inches. | In Progress | New
023 | 2.3.8 | low power consumption, performance | The power consumption of the application shall not drain the iPhone battery more than 10% when run continuously for 30 minutes. | In Progress | 2.3.6
024 | 2.3.9 | integrity | The software shall have the flexibility to operate on the iPhone operating system without interrupting the system’s normal operation. | In Progress | New
025 | 2.3.10 | security | The software security shall allow no more than 1 user to be connected to a personal profile at any given time. | In Progress | 2.3.8
026 | 2.3.11 | compatibility | The software shall synchronize calendar information from internet connected devices without interrupting normal operation of the connected devices. | In Progress | New
027 | 2.3.12 | security | The software security shall allow a user to access his or her unique profile while blocking access to the profile from unintended users. | In Progress | 2.3.6
028 | 2.3.13 | modifiability | The software security feature shall be modifiable by the user in order to change personal information and accessibility. | In Progress | 2.3.10
029 | 2.3.14 | maintenance | The software maintenance shall be applied using software updates through a wireless connection. | In Progress | 2.3.11
030 | 2.3.15 | maintainability | Software maintainability shall be applied wirelessly through an internet connection. | In Progress | 2.3.11 duplicate
031 | 2.3.16 | fault tolerance, performance | The software reliability shall allow continuous operation for 1 hour without encountering a software fault. | In Progress | New
032 | 2.3.17 | error handling, performance | The software error handling shall notify the user of an error once it is identified. | In Progress | New
033 | 2.3.18 | ease of use, performance | The software shall have an ease of use that allows scheduling operations to be completed within a reasonable amount of time. | In Progress | 2.3.14
034 | 2.3.19 | correctness | The software shall output correct scheduling information from communicable devices such that misinterpretation of the data is minimal. | In Progress | 2.3.15
035 | 2.3.20 | compatibility | The software shall be compatible with the following calendars: Outlook, Google, Yahoo, and Lotus Notes. | In Progress | moved from functional
VERSION 3
036 | 2.3.1 | compatibility | The software shall be compatible as an application on the Apple iPhone version 3GS and newer. | In Progress | 2.3.1 v2 |  |  |  | 2.3.1 |  |  | Test
037 | 2.3.2 | availability | The software shall be available for download from the iPhone App Store. | In Progress | 2.3.2 v2 |  |  |  | 2.3.2 |  |  | Test
038 | 2.3.3 | compatibility | The filesize of the application shall not exceed the maximum limit for iPhone apps transmitted over a 3G connection. | In Progress | 2.3.3 v2 |  |  |  | 2.3.3 |  |  | Test
039 | 2.3.4 | usability | The software shall be understandable to users who perform scheduling functions on a daily basis. | In Progress | 2.3.4 v2 |  |  |  | 2.3.4 |  |  | Beta Test
040 | 2.3.5 | usability | The software functions shall be accessible through a GUI application interface. | In Progress | 2.3.5 v2 |  |  |  | 2.3.5 |  |  | Test
041 | 2.3.6 | usability | The GUI application interface shall have an ease of use such that the user can begin performing operations without prior training or exposure to the application. | In Progress | 2.3.6 v2 |  |  |  | 2.3.6 |  |  | Beta Test
042 | 2.3.7 | usability | The GUI application interface shall have readable text such that a user with 20/20 eyesight or corrected vision can read the text in ambient lighting from a distance of 6 inches to 24 inches. | In Progress | 2.3.7 v2 |  |  |  | 2.3.7 |  |  | Beta Test
043 | 2.3.8 | low power consumption, performance | The power consumption of the application shall not drain the iPhone battery more than 10% when run continuously for 30 minutes. | In Progress | 2.3.8 v2 |  |  |  | 2.3.8 |  |  | Test
044 | 2.3.9 | integrity | The software shall have the flexibility to operate on the iPhone operating system without interrupting the system’s normal operation. | In Progress | 2.3.9 v2 |  |  |  | 2.3.9.a/b/c |  |  | Test
045 | 2.3.10 | security | The software security shall allow no more than 1 user to be connected to a personal profile at any given time. | In Progress | 2.3.10 v2 |  |  |  | 2.3.10 |  |  | Test
046 | 2.3.11 | compatibility | The software shall synchronize calendar information from internet connected devices without interrupting normal operation of the connected devices. | In Progress | 2.3.11 v2 |  |  |  | 2.3.11 |  |  | Test
047 | 2.3.12 | security | The software security shall allow a user to access his or her unique profile while blocking access to the profile from unintended users. | In Progress | 2.3.12 v2 |  |  |  | 2.3.12 |  |  | Analysis
048 | 2.3.13 | modifiability | The software code shall be modifiable in order for a programmer to make a minor change to the code easily and without changing the software functionality. | In Progress | re-written from 2.3.13 v2 |  |  |  | 2.3.13 |  |  | Test
049 | 2.3.14 | maintenance | The software maintenance shall be applied directly to the server location on the cloud. | In Progress | changed from 2.3.14 v2 |  |  |  | 2.3.14 |  |  | Test
050 | 2.3.15 | maintainability | The software code shall be maintainable in order for a programmer to fix a bug in the code easily and without changing the software functionality. | In Progress | re-written from 2.3.15 v2 |  |  |  | 2.3.15 |  |  | Test
051 | 2.3.16 | fault tolerance, performance | The software reliability shall allow continuous operation for 1 hour without encountering a software fault. | In Progress | 2.3.16 v2 |  |  |  | 2.3.16 |  |  | Test
052 | 2.3.17 | error handling, performance | The software error handling shall notify the user of an error 2 seconds from detection. | In Progress | 2.3.17 v2 |  |  |  | 2.3.17 |  |  | Test
053 | 2.3.18 | ease of use, performance | The software shall have an ease of use that allows scheduling operations to be completed within a reasonable amount of time. | In Progress | 2.3.18 v2 |  |  |  | 2.3.18 |  |  | Beta Test
054 | 2.3.19 | correctness, interoperability | The software shall output correct scheduling information from communicable devices such that misinterpretation of the data is minimal. | In Progress | 2.3.19 v2 |  |  |  | 2.3.19 |  |  | Test
055 | 2.3.20 | compatibility | The software shall be compatible with the following calendars: Outlook, Google, Yahoo, and Lotus Notes. | In Progress | 2.3.20 v2 |  |  |  | 2.3.20 |  |  | Test
VERSION 4
056
057
058
059
060
061
062
063
064
065
066
067
068
069
070
071
072
073
074
075
Note on A6: • ID: A unique ID number used to identify the requirement in the requirement traceability log.
Note on B6: • Assoc ID: This column should contain the ID of any associated utilities used for requirements tracking such as a repository, pipeline document, etc.
Note on C6: • Technical Assumptions or Customer Needs: This column should be populated with a description of the technical assumption or customer need linked to the functional requirement.
Note on D6: • Non-Functional Requirement: This column should be populated with a description of the non-functional requirement.
Note on E6: • Status: This column should be populated with the current status of the functional requirement.
Note on F6: 1053480: Indicate which requirement the new/updated requirement is traced to.
Note on G6: • Technical Specification: This column should be populated with a description of the technical specification linked to the functional requirement.
Note on H6: • System Component(s): This column should be populated with a description of the system component(s) linked to the functional requirement.
Note on I6: • Software Module(s): This column should be populated with a description of the software module(s) linked to the functional requirement.
Note on J6: • Test Case Number: This column should be populated with the test case number linked to the functional requirement.
Note on K6: • Tested In: This column should be populated with the module that the functional requirement has been tested in.
Note on L6: • Implemented In: This column should be populated with the module that the functional requirement has been implemented in.
Note on M6: • Verification: This column should be populated with a description of the verification document linked to the functional requirement.